## Slide 1: Seafield WwTW Strategic Odour Review
28th September 2018

## Slide 2: Check on Progress of Recommended Measures Implementation

## Slide 3
12 short-term measures – Seafield & Network;
  4 engineering feasibility studies
  Contingency dosing plan
  2 ventilation & air balance flow investigations
  Intermediate wastewater treatment
  Wallyford Nutriox dosing
  H2S Monitoring
  Further septicity investigations
  Ropeworks vent chimney
Summary of March 2018 Report Recommendations

## Slide 4
4 medium-term measures;
  Conversion of storm tanks
  Redevelopment of sludge cake building
  Additional sludge storage capacity
  Replace PSTs
All dependent upon outcomes of engineering feasibility studies
Summary of March 2018 Report Recommendations

## Slide 5
2 long-term measures;
  Vision & strategy for a re-developed, sustainable Seafield site
  Relocate wastewater and sludge treatment to a new location
Both of the above also dependent upon outcomes of feasibility studies and other, wider Edinburgh-wide and national population growth matters
Summary of March 2018 Report Recommendations

## Slide 6
7 operational improvement measures;
  Additional on-site H2S monitoring and limit values
  Annual odour emissions surveys
  Improved weather forecasting system
  HAZOP-type approach for process change odour risks
  Tanker driver odour awareness training
  Internal workshops to enhance OMP
Summary of March 2018 Report Recommendations

## Slide 7
3 communications improvement measures;
  More interactive and meaningful web site
  Real-time odour dispersion model display
  Enhanced complaints handling & response system
Summary of March 2018 Report Recommendations

## Slide 8: What is the state of progress on these measures?

## Slide 9
12 short-term recommendations;
  1 completed (Wallyford);
  8 have been commissioned and are under way, with reporting dates in October/November 2018;
  1 assessed in detail and rejected (MEPS ferric dosing)
  2 to be started (Ropeworks & further septicity surveys)
Summary of Progress Status September 2018

## Slide 10
4 medium-term measures;
  All dependent upon the outcomes of engineering feasibility studies
Summary of Progress Status September 2018

## Slide 11
2 long-term measures;
  Both in the early stages of pre-feasibility
  Dependent upon the outcomes of engineering feasibility studies and further consideration of Edinburgh-wide and national population growth and development
Summary of Progress Status September 2018

## Slide 12
7 operational improvement measures;
  1 completed (Tanker drivers’ training)
  5 under way
  1 under review (odour surveys)
Summary of Progress Status September 2018

## Slide 13
3 communications improvement measures;
  All 3 under way
Summary of Progress Status September 2018

## Slide 14
5 completed
17 in progress
6 to be commenced (4 dependent upon outcome of feasibility studies)
Summary of Progress Status September 2018

## Slide 15
Dosing trials with KMnO4
  To be carried out at SWH facility at Bo’ness
  Commencing 1/10/2018 for 4/5 weeks
Further investigation of the sewer network around Seafield feeding-into the Siphon House
“Bow-Tie” risk analysis of proposed process changes
Additional Items

## Slide 16
Thank you